Project Status Report: Onboarding New Clients to Financial Product

Project Objective

To successfully onboard 25 new Clients our new financial product.

Progress This Week

• We have onboarded IO new clients this week, bringing the total to 15.

- Conducted initial setup and training sessions for each client.

- Received positive feedback on the user interface and initial functionality Of the    product.

- Enhanced the client onboarding manual based on early feedback, improving clarity on some Procedures.

New Risks

• Risk of Delays in Client Data Integration:

- We've identified potential delays in integrating client data due to varying formats provided by the clients.

- Proposed Solution: Implement a standardized data format requirement and provide clients With a template to expedite the process.

Outstanding Items

• Complete Onboarding for Remaining 10 Clients:

- Scheduled sessions for the upcoming week.

- Preparing additional support material to address common questions raised by the first 15 Clients.

• Client Data Integration for Newly Onboarded Clients:

- Continue working with our IT team to resolve format discrepancies in client data.

• Feedback Collection and Implementation:

- Plan to send out a feedback form post-onboarding to gather insights and improve the

process further.

Next Steps

• Focus on enhancing the client onboarding process by incorporating feedback and standardizing data integration practices.

- This will likely improve client satisfaction and reduce onboarding times.

• Monitor the resolution of data integration issues closely.

- Any delays in this area could affect our project timeline and client satisfaction.